DETAILED REVIEW OF YOUR IMPLEMENTATION PLAN

Swiggy vs Zomato Social Product Intelligence Project

Phase Analysis | Issues Found | Corrections Required | Optimized Timeline

# EXECUTIVE SUMMARY

Your 15-phase plan is GOOD overall but has 5 CRITICAL ORDERING ISSUES that will cause rework. Correcting these will save 3-4 weeks of development time and prevent rebuilding components.

# ✓ What's WORKING Well in Your Plan

- Phase 0 (Environment Setup) — Comprehensive and correct first step

- Phase 1 (Data Collection) — Well-structured, correct approach

- Phase 2 (Data Cleaning) — Proper placement after collection

- Phase 3 (Sentiment Analysis) — Right foundation for NLP work

- Phase 11 (Airflow Automation) — DAG structure is well-designed

- Phase 12-15 (Dockerization → Optimization) — Proper deployment sequence

- Overall dependency understanding — You correctly identify that phases must be sequential

# ✗ CRITICAL ISSUES FOUND

## ISSUE #1: Database Design is Implicit (Not a Formal Phase)

Your plan mentions creating raw_mentions table in Phase 1, but there's no dedicated comprehensive database design phase.

Current state:

- Phase 1 mentions: CREATE TABLE raw_mentions

- Phase 3 mentions: CREATE TABLE processed_mentions

- Phase 4 mentions: CREATE TABLE sentiment_results (implied)

- Aspect results table? → Not mentioned

- Topic results table? → Not mentioned

- Daily scores table? → Not mentioned

- Elasticsearch mapping? → Phase 9 (too late)

Problem: You'll reach Phase 4 and realize you need a sentiment_results table. Then Phase 5 you need aspect_results, Phase 6 you need topic_results. This causes multiple database migrations and downstream code changes.

## ISSUE #2: Dashboard MVP (Phase 4) Placed BEFORE Scoring (Phase 7)

This is your biggest ordering mistake.

Current sequence:

Phase 3: Sentiment Analysis

Phase 4: Dashboard MVP ← DASHBOARD BUILT

Phase 5: ABSA

Phase 6: Topic Modeling

Phase 7: Intelligence Scoring ← SCORING HAPPENS LATER

The Problem: In Phase 4 you build dashboard with basic sentiment charts. Then in Phase 7 you create composite intelligence scores. Now you must REDESIGN the dashboard (Phases 4-6 wasted). Professional teams build UI LAST, not first.

## ISSUE #3: Elasticsearch Integration (Phase 8) Should Be Earlier

Elasticsearch is a data layer, not a presentation layer.

Current sequence:

- Phase 3: Sentiment results in PostgreSQL

- Phase 4-7: More data added to PostgreSQL

- Phase 8: NOW index everything in Elasticsearch

- Problem: Phase 4 dashboard queries slow PostgreSQL without search optimization

## ISSUE #4: Testing Only at End (Phase 14)

Testing should happen throughout development, not just at the end.

- Phase 14 testing happens AFTER full system built

- If Phase 3 sentiment model has bugs, you discover it in Phase 14 (11 phases too late!)

- Professional approach: write unit tests for each collector, each NLP model, each scoring function

## ISSUE #5: Missing Phase for Configuration Management

You mention defining aspects, keywords, thresholds but there's no formalized phase.

- Where do you define aspect list? Buried in Phase 5 instructions

- Where do you define alert thresholds? Buried in Phase 9 instructions

- Where do you define scoring weights? Buried in Phase 7 instructions

- Result: Config scattered across code instead of centralized

# RECOMMENDED CORRECTIONS

## Correction #1: Add Phase for Comprehensive Database Design

Insert BEFORE Phase 1 (Data Collection):

Phase 0.5 (NEW): Database Schema & API Design

Design & Create:

├── raw_mentions          (raw data from internet)

├── processed_mentions    (cleaned text)

├── sentiment_results     (sentiment labels + confidence)

├── aspect_results        (ABSA outputs)

├── topic_results         (topic modeling outputs)

├── daily_brand_scores    (composite intelligence scores)

├── alerts_log            (alert history)

└── elasticsearch_mapping (search index schema)

Time: 2 days. Benefit: Avoid 3 emergency migrations later.

## Correction #2: Move Dashboard to AFTER Scoring

New sequence:

Phase 3: Sentiment Analysis

Phase 4: ABSA (was Phase 5)

Phase 5: Topic Modeling (was Phase 6)

Phase 6: Intelligence Scoring (was Phase 7)

Phase 7: Elasticsearch Indexing (was Phase 8)

Phase 8: Dashboard MVP (was Phase 4) ← BUILD DASHBOARD LAST

Benefit: You build dashboard ONCE with complete intelligence data. No redesign needed. Dashboard is built when you know exactly what data you're visualizing.

## Correction #3: Move Elasticsearch Earlier in Timeline

Current (Phase 8) → New (Phase 5.5 / right after Sentiment)

Phase 3: Sentiment complete

Phase 4: ABSA

Phase 5: Topic Modeling

Phase 5.5 (NEW): Elasticsearch Indexing ← Index ALL processed data

Phase 6: Intelligence Scoring

Phase 7: Dashboard (now with fast search)

## Correction #4: Add Testing Throughout, Not Just at End

Integrate into each phase:

Phase 1: Data Collection

└─ Test: 5 collectors working, 100+ samples collected ✓

Phase 2: Data Cleaning

└─ Test: Unit tests for cleaner.py, 10 edge cases ✓

Phase 3: Sentiment Analysis

└─ Test: Model F1 > 0.80 on 50-sample validation set ✓

...and so on

Phase 13 (FINAL): Integration testing ← Only integration tests here

## Correction #5: Add Phase for Configuration Management

New Phase 0.25 (after Environment, before Database):

Phase 0.25 (NEW): Configuration & Watchlist Management

Create centralized config/:

├── watchlist.json        (keywords for Swiggy/Zomato)

├── aspects.json          (ABSA aspect definitions)

├── thresholds.json       (alert triggers)

├── scoring_weights.json  (composite score formula)

├── sources.json          (data source configs)

└── settings.py           (all env variables)

Benefit: All business logic (keywords, aspects, thresholds) is defined in config files, not hardcoded in Python. Easy to update without touching code.

# OPTIMIZED 14-PHASE TIMELINE

Incorporates all corrections. Total: ~14 weeks.

| Phase | Name | Key Deliverable | Weeks | Status |
| --- | --- | --- | --- | --- |
| 0 | Environment & Config Setup | venv, Docker, requirements.txt, config files | 1 | ✓ UNCHANGED |
| 0.5 | Database Schema Design (NEW) | All 7 tables created, indexes added, backups tested | 0.5 | ✓ INSERT HERE |
| 1 | Data Collection | All 7 collectors working, 500+ samples | 2 | ✓ MOVED |
| 2 | Data Validation & Cleaning | Processed text, duplicates removed, quality checked | 1.5 | ✓ MERGED |
| 3 | Sentiment Analysis | Model loaded, batch inference working, F1 > 0.80 | 1.5 | ✓ UNCHANGED |
| 4 | ABSA (Aspect-Based) | Aspects extracted per definition, stored in DB | 1.5 | ✓ MOVED UP |
| 5 | Topic Modeling | LDA/BERTopic generating weekly topics, coherence checked | 1.5 | ✓ MOVED UP |
| 6 | Intelligence Scoring | Composite scores: (0.4S + 0.3R + 0.2V + 0.1T) | 1 | ✓ MOVED UP |
| 7 | Elasticsearch Indexing | All processed data indexed, search working | 1 | ✓ MOVED UP |
| 8 | Dashboard MVP | 5 tabs: Overview, Sentiment, Features, Topics, Raw Feed | 2 | ✓ MOVED UP (after all data ready) |
| 9 | Alert System | Slack/email alerts firing on sentiment spikes | 1 | ✓ UNCHANGED |
| 10 | Report Generation | Weekly PDF auto-generated, emailed | 1 | ✓ UNCHANGED |
| 11 | Airflow Automation | DAG running end-to-end daily, 5-day test pass | 1.5 | ✓ UNCHANGED |
| 12 | Dockerization | docker-compose up works, all services healthy | 1 | ✓ UNCHANGED |
| 13 | Deployment & Testing | Prod-ready, performance tested, scaling verified | 1 | ✓ MOVED |
| 14 | Monitoring & Optimization | Logging, metrics, dashboards, edge case handling | 0.5 | ✓ ONGOING |

# Before vs After Comparison

| Aspect | YOUR PLAN (15 Phases) | OPTIMIZED PLAN (14 Phases) |
| --- | --- | --- |
| Database Design | Implicit in Phase 1 | Explicit Phase 0.5 |
| Dashboard Placement | Phase 4 (too early, before scoring) | Phase 8 (after all intelligence ready) |
| Elasticsearch | Phase 8 (too late) | Phase 7 (earlier, data layer) |
| Testing Strategy | Phase 14 only (end-of-cycle) | Integrated throughout (continuous) |
| Configuration Mgmt | Scattered in instructions | Phase 0 (centralized config files) |
| Time Savings | — | 3-4 weeks (avoid rework) |

# Detailed Changes Required (Phase by Phase)

## Phase 0: Environment & Config Setup

Change: Expand to include creating centralized config files (watchlist.json, aspects.json, thresholds.json, scoring_weights.json). Not just Python environment.

## Phase 0.5 (NEW): Database Schema Design

This phase must be added. Create comprehensive schema:

Tables to design:

1. raw_mentions (text, rating, source, external_id, ...)

2. processed_mentions (cleaned_text, language, ...)

3. sentiment_results (sentiment_label, confidence, mention_id, ...)

4. aspect_results (aspect, sentiment, confidence, mention_id, ...)

5. topic_results (topic_id, keywords, weight, mention_id, ...)

6. daily_brand_scores (brand, score_date, composite_score, ...)

7. alerts_log (alert_type, message, fired_at, ...)

8. elasticsearch_mapping (index schema JSON)

Tasks:

- Write schema DDL (CREATE TABLE statements)

- Design indexes for performance (external_id, brand, post_date, etc.)

- Design foreign keys if using relational integrity

- Plan backup strategy

- Document schema (draw ER diagram)

## Phase 1: Data Collection (Minor Update)

Change: Add data quality checks: verify external_id is unique, check for NULL text, validate timestamps. This ensures clean data enters Phase 2.

## Phase 2: Data Cleaning & Validation

Change: Consolidate your Phase 2 (Data Cleaning) + validation here. Add: deduplication logic, language detection, emoji normalization. Output: processed_mentions table fully populated.

## Phase 3: Sentiment Analysis (Unchanged)

Load model, run batch inference, store sentiment_results. ✓ Correct placement.

## Phase 4: ABSA (Moved from Phase 5)

Change: Move up (was Phase 5). Build on sentiment results. Output: aspect_results table.

## Phase 5: Topic Modeling (Moved from Phase 6)

Change: Move up (was Phase 6). Run LDA/BERTopic. Output: topic_results table.

## Phase 6: Intelligence Scoring (Moved from Phase 7)

Change: Move up (was Phase 7). Compute composite scores using formula: 0.4×sentiment + 0.3×rating + 0.2×volume + 0.1×trend. Output: daily_brand_scores table.

## Phase 7: Elasticsearch Indexing (Moved from Phase 8)

Change: Move up (was Phase 8). Index ALL processed data from sentiment, ABSA, and topics into Elasticsearch. Now dashboard queries are fast.

## Phase 8: Dashboard MVP (Moved from Phase 4) — MAJOR CHANGE

This is your biggest fix. Build dashboard AFTER all intelligence is ready.

Now dashboard has complete data:

- Sentiment scores (from Phase 3) ✓

- Aspect sentiments (from Phase 4) ✓

- Topic clusters (from Phase 5) ✓

- Intelligence scores (from Phase 6) ✓

- Elasticsearch index (from Phase 7) ✓

Build dashboard with full understanding of data structure. No redesign needed later.

## Phase 9-13: Unchanged

Alerts → Reports → Airflow → Docker → Deployment. Sequence is good.

# Testing Strategy (Integrated, Not End-of-Cycle)

Instead of Phase 14 testing, integrate into each phase:

| Phase | Component | Test Strategy |
| --- | --- | --- |
| 1 | Data Collectors | Unit tests: each collector returns expected schema, 10+ samples collected |
| 2 | Text Cleaner | Unit tests: emoji handling, URL removal, edge cases (short text, special chars) |
| 3 | Sentiment Model | Validation: F1 > 0.80 on labelled 50-sample test set |
| 4 | ABSA | Validation: manual inspection of 20 aspect extractions, precision > 0.75 |
| 5 | Topic Model | Validation: topic coherence score > 0.5, manual review of top 5 topics |
| 6 | Scoring Formula | Unit tests: verify score range (-1 to +1), test edge cases (zero volume, null rating) |
| 7 | Elasticsearch | Integration test: 100 docs indexed, search queries return correct results |
| 8 | Dashboard | Smoke test: all 5 tabs load, charts render, no 500 errors |
| 13 | Full System | End-to-end: data collection → sentiment → dashboard in 1 hour |

FINAL VERDICT
Your 15-Phase Plan: GOOD FOUNDATION but NEEDS CORRECTIONS
With changes applied: EXCELLENT ROADMAP
Recommended Action: Follow the 14-phase OPTIMIZED plan above

## Summary of Changes

- ✓ Add Phase 0.5: Database Schema Design (prevents 3 migrations)

- ✓ Move Dashboard from Phase 4 → Phase 8 (build UI after intelligence)

- ✓ Move Elasticsearch from Phase 8 → Phase 7 (data layer, not presentation)

- ✓ Integrate Testing throughout (unit tests in each phase, not Phase 14)

- ✓ Add Phase 0: Configuration Management (centralize keywords, aspects, thresholds)

Implement these 5 changes and your project execution becomes world-class. Without them, you'll lose 3-4 weeks to rework.

— End of Review —